## Sheet1
Tasks | Duration | Predecedors
Create software Archit (A) | 3 | -
Review Software Archit (B) | 2 | Create software Archit
get initial feedback from users ( c ) | 6 | A,B
Test Web App for Supleirs ( D) | 4 | A,B
Team Appraisal ( E ) | 3 | A,B,C,D
Document of unResolved issues (F) | 1 | D,C