## Sheet1
1 Plan
1.1 Create Stakeholders Engagment Plan
1.2 Create StakeHolders Communication Plan
1.3 Create Team Charter
2 Design
2.1 create software Architecture
2.2 Review Software Archit
3 Implement
3.1 Develop Mobile app for users
3.2 Develop Website for suppliers and vendors to be partners
4 Test
4.1 Test Mobile app that would be used by users
4.2 Test Web App used by suppliers or vendors
5 Deploy
5.1 Deploy mobile app in one platfrom first as a test and get feedback from users
5.2 allow a specific numbers of partners first as a test and add others in the waiting list
5.3 deploy mobile app to all stores after ensuring it went well
5.4 Add suppliers from waiting list and approve them to be partners
5.5 Launch a web app for users
6 Closure
6.1 Team appraisal
6.2 Document of lists of unresolved issues
6.3 updates phases