## Sheet1
1 Plan |  | Estimated Cost
1.1 Create Stakeholders Engagment Plan |  | 50
1.2 Create StakeHolders Communication Plan |  | 50
1.3 Create Team Charter |  | 100
| Total | 200
2 Design
2.1 create software Architecture |  | 200
2.2 Review Software Archit |  | 200
| Total | 400
3 Implement
3.1 Develop Mobile app for users |  | 2000
3.2 Develop Website for suppliers and vendors to be partners |  | 2000
4000
4 Test
4.1 Test Mobile app that would be used by users |  | 1500
4.2 Test Web App used by suppliers or vendors |  | 1500
| Total | 3000
5 Deploy
5.1 Deploy mobile app in one platfrom first as a test and get feedback from users |  | 500
5.2 allow a specific numbers of partners first as a test and add others in the waiting list |  | 100
5.3 deploy mobile app to all stores after ensuring it went well |  | 1000
5.4 Add suppliers from waiting list and approve them to be partners |  | 2000
5.5 Launch a web app for users |  | 2000
| Total | 5600
6 Closure
6.1 Team appraisal |  | 2000
6.2 Document of lists of unresolved issues |  | 200
6.3 updates phases |  | 300
| Total | 2500
| Final Estimation Cost | 11700
plan made for wbs input and costs are just estimated not actual real cost may vary on market price and expert view