## Sheet1
Description of Risk | Impact Description | Probability | Impact | Risk Rating | Mitgation Strategy | RiskPlan | Risk Owner | Status
Servers Failure | Stopping of all Services | Very Likely | Extreme | High | Avoid | 1- use cloud services such AWS or Google Cloud | Customer
Simlar Tech Companies cloning the project | high competance | likely | high | moderate | Accept | ensure special offers with contracts with partners | Customer
Team Issues | waste of time and resources | Very Likely | high | moderate | Mitigate | ensure best communicaton between all parties and solve issues as soon as possible | PM
Global Pandemic | Stopping of all Services | unlikely | Extreme | High | Avoid | back up plan such as remote working , and taking all precautions | Customer
partners issues | not following the contract | unlikely | Extreme | moderate | Mitigate | meetings with them to ensure smooth operations | Customer