## Sheet1
StakeHolder Engagement assessment matrix
StakeHolder | Unaware | Resistant | Neutral | Supportive | Leading
Users |  |  | C | D C
Owner |  |  |  | D C | D
Partners(suppliers) |  | C |  | D
Marketing Team |  |  |  | D C
Accounting Team |  |  |  | D
Payment Service Partners(banks) |  |  | C | D
Government |  | C |  | D
Development Team(my team) |  |  |  | C
My plan to move stakeHolders in the matrix
users : communicate more with them and try to make votes on their prefered resturants and shops
partners: make a marketing plan to try to engage more partners that my users are already interested in also convice partners to give better offers
Marketing Team : Need to motivate them better to make them supportive and think out of the box
Payment Services: try to get a branded credit card from banks with special offers and execlusicve prices
Government: facilitate paper work
Communication Management Plan
Message/Purpose | Responsibility | Audience | Medium | Contents | Frequency/Timing
Get Recommendations | Customer Service | Users | Email/App feedback | votes/suggestions | Bi-Weekly
Project Review | PM | Owner | Meeting/Email | Risks,Progress,plan | Weekly
Reach More Partners | Marketing Team/SalesTeam | Partners(suppliers) | Meeting/Email | strategy,benefits | Daily
Marketing Campagins | Marketing Team | MarketingTeam | SocialMedia | offers/benefits | Weekly
Audit | QA | AccountingTeam | Meeting/Email | compliance,issues,risks | Monthly
Audit/Status | Accounting Team | Banks | Meeting/Calls/Emails | Compliance,issues,risks | Monthly
Audit | PM | Government | Meetings | issues,Risks | Monthly
Reports | PM | Development Team | Meetings/Emails | progress/issues/Testing | Daily StandUPS/Weekly